...COLUMNWIDT� 45

Programmin� the

Performance Evaluation and Review �echnique (PERT)

i� BASIC

"� metho� fo� plannin� comple� activitie�

wher� n� precedent� exist."

Origina� progra� b� Steve� Zimmerma� an� Le� M� Conrad

Develope� an� modifie� fo� th� Osborn� � b� Dou� Hurst

Tex� an� progra� listin� reprinte�

fro� BYT� Magazin� wit� permission.

#TABLE OF CONTENTS#

#Osborn� � Prolog# . . . . . . . . . . .    2

#Introduction.#  . . . . . . . . . . . .    3

#Origin� o� PERT.# . . . . . . . . . . .    3

#Th� Star� o� PER� Analysis.#  . . . . .    3

#Th� Bubbl� Diagram.#  . . . . . . . . .    4

#Th� Critica� Path.# . . . . . . . . . .    4

#Thre� Tim� Estimates.#  . . . . . . . .    5

#Ou� PER� Program.#  . . . . . . . . . .    5

#Runnin� th� Program.# . . . . . . . . .    6

#Conclusion#.  . . . . . . . . . . . . .    8

#Figur� 1#  . . . . . . . . . . . . .    9

#Tabl� 1# . . . . . . . . . . . . . .   10

#� Glanc� a� th� Mathematic� o� PERT#   11

�                    Programmin� PER� i� BASIC

"� metho� fo� plannin� comple� activitie�

wher� n� precedent� exist."

Origina� progra� b� Steve� Zimmerma� an� Le� M� Conrad

Develope� an� modifie� fo� th� Osborn� � b� Dou� Hurst

Tex� an� progra� listin� reprinte�

fro� BYT� Magazin� wit� permission.

...T1

#Osborn� � Prolog#

Th� BYT� articl� fro� whic� thi� librar� submissio� wa� �

extracte� appear� o� page� 465-47� o� th� Ma� 198� issu� wit� th� �

them� "Japanes� Computers�

Thi� wa� � fairl� eas� progra� t� conver� t� ru� o� th� O-�

a� ar� mos� program� writte� i� TRS-8� Leve� I� o� Dis� �

Basic(als� b� MicroSoft)� Deletion� t� th� progra� includ� al� �

tap� sav� an� loa� routines� Addition� includ� � mean� b� whic� �

t� designat� tim� unit� use� an� projec� star� date� a� wel� a� �

thei� appearanc� o� th� har� cop� output� Also� an� mos� �

important� i� th� inclusio� o� th� abilit� t� displa� an� �

printou� � GANN� Char� o� th� pertinen� PER� elements.

Th� progra� ha� grea� practica� utility�  A� th� Marin� �

Corp� Communication-Electronic� School� Twentynin� Palms� CA� w� �

ar� involve� i� � larg� numbe� o� coursewar� conversion� (t� �

Compute� Aide� Instruction(CAI)� tha� ar� sprea� out� i� som� �

cases� ove� period� a� larg� a� years� PER� ha� bee� instrumenta� �

i� bot� th� plannin� an� monitorin� o� thes� projects.

Ther� ar� no� � mai� program� o� th� diskette� PERTSAMP.COM� �

PERT80.BAS� an� PERT128.BAS� PERTSAMP.CO� i� somethin� I'� reall� �

prou� of� althoug� � can'� tak� ful� credi� fo� th� originality� �

� pulle� � progra� calle� OSBOARD1.CO� of� Kell� Smith'� CP/� Ne� �

� whil� back� I� wa� reall� a� advertisemen� fo� � progra� whic� �

make� th� O-1'� graphic� eas� t� use� I� doin� s� i� showe� th� �

program'� capability� PERTSAMP.CO� doe� muc� th� same� Jus� plac� �

th� PER� diskett� i� th� � driv� an� hi� th� return�

IMPORTAN� � Mak� sur� yo� printe� i� u� whe� yo� d� so�

Wha� yo� wil� ge� i� � complet� sampl� ru� o� th� PER� progra� �

includin� printouts� Yo� shoul� d� thi� righ� awa� eve� thoug� �

PER� hasn'� eve� bee� explaine� yet�  Th� � page� o� outpu� ar� �

Listing� 2,3,4,an� � a� referre� t� i� th� articl� proper� �

PERTSAM� i� compile� BASIC� PERT80/128.BA� ar� name� base� o� �

thei� printe� requirements� TEM� i� merel� � fil� whic� yo� ma� �

read into the program for practice.

Wit� th� lates� addition� tha� is- th� GANN� Chart� thi� �

PER� progra� i� swiftl� approachin� th� qualit� o� MILESTON� (o� �

th� Osborn� Approve� Softwar� list� Organi� Software� Retai� �

Pric� $295.00)�

�(Note� M� friend� fo� th� tim� being� Jerr� Lawson� ha� bee� �

ploddin� awa� a� PERT'� companio� progra� "Programmin� th� �

Critica� Pat� Metho� i� BASIC"� (BYTE� Jul� 1982� page� 378-390� �

fo� quit� som� tim� now� � force� hi� t� d� i� becaus� s� muc� �

ca� b� learne� abou� programin� fro� th� copyin� an� debuggin� �

process� It'� bee� � slo� proces� an� beside� h� ha� � wif� an� �

famil� t� whic� h� i� mor� devote� tha� hi� Osborne� Can'� �

understan� that� Whe� h� finishe� hi� part� th� progra� wil� b� �

cleane� up� modifie� an� submitted� Onc� thi� i� done� MILESTON� �

wil� hav� bee� equaled.�

...T1

#Introduction.#

Th� Performanc� Evaluatio� an� Revie� Techniqu� (PERT� i� � �

powerfu� metho� o� plannin� comple� activities� especiall� �

pioneerin� project� lik� th� creatio� o� � ne� busines� o� th� �

developmen� o� � ne� machine� Th� innovativ� natur� o� thes� �

project� assure� tha� fe� precedent� exis� t� hel� estimat� �

performanc� time.

PER� give� manager� th� tool� t� dea� wit� uncertainty� PER� �

i� managemen� i� action�  I� plans� schedules� an� control� �

activity� Usin� PERT� contractors� builders� engineers� an� �

businessme� ca� improv� plannin� i� th� mids� o� uncertaint� an� �

sav� mone� a� � result.

Unti� now� onl� larg� businesse� wit� acces� t� larg� �

computer� coul� us� PERT� Th� progra� i� listin� � (Listin� � ma� �

b� obtaine� b� loadin� eithe� PERT80.BA� o� PERT128.BAS� settin� �

WIDT� LPRIN� 80� an� the� doin� � LLIST.� bring� PERT'� powe� t� �

microcompute� users�

Befor� presentin� ou� program� however� we'l� giv� yo� � �

glimps� a� PERT'� history� briefl� describ� th� natur� o� PER� �

analysis� sugges� on� possibl� PER� applicatio� fo� � manager� �

an� examin� th� mathematic� behin� PERT.

...T1

#Origin� o� PERT.#

PER� date� bac� t� � tea� create� b� th� Nav� Specia� �

Project� Office� Lockhee� Aircraf� Corporation� an� managemen� �

consultin� fir� o� Booz� Allen� an� Hamilton� Wor� durin� Worl� �

Wa� � o� th� Gann� schedulin� char� an� th� Gann� mileston� char� �

shoul� als� b� note� becaus� thes� precipitate� th� developmen� �

o� th� networ� diagra� (describe� later� use� i� PERT.

Manager� o� man� differen� kind� o� task� hav� successfull� �

applie� PERT� On� particularl� spectacula� resul� o� th� PER� �

approac� i� th� Polari� missile� whic� als� occasione� PERT'� �

development� (Lockhee� Aircraf� wa� th� majo� contracto� fo� �

Polaris.� Completio� tim� wa� critica� i� th� Polari� program� �

bu� ther� wa� considerabl� uncertaint� abou� ho� lon� th� �

require� activitie� woul� take�  Moreover� th� star� o� man� �

activitie� depende� o� th� completio� o� others� Thes� ar� th� �

chie� reason� wh� PER� employ� � networ� schem� an� focuse� o� �

th� probabilit� o� variou� activitie� finishin� a� specifie� �

times.

...T1

#Th� Star� o� PER� Analysis.#

PER� analysi� begin� b� reducin� � projec� descriptio� t� � �

lis� o� event� an� activities�  A� activit� i� � par� o� � ��projec� tha� consume� resource� o� tim� an� ha� � definabl� �

beginnin� an� end� A� even� i� � poin� i� time� instant� Th� �

beginnin� an� endin� point� o� a� activit� ar� events� T� appl� �

PER� t� � comple� project� yo� mus� identif� al� th� event� �

neede� t� complet� th� projec� an� al� th� activitie� tha� resul� �

i� th� identifie� events.

A� a� example� we'l� us� � simplifie� versio� o� a� actua� �

constructio� projec� tha� w� jus� completed� T� simplify� we'l� �

en� ou� exampl� wit� th� completio� o� th� building'� foundation� �

W� identifie� 1� activitie� neede� t� complet� thi� foundation� �

Tabl� � list� th� activities� assigne� letter� � throug� � an� Z� �

Eac� o� th� nin� event� i� th� projec� consist� o� th� completio� �

o� on� o� mor� activities.

...T1

#Th� Bubbl� Diagram.#

Th� secon� stag� i� PER� analysi� i� th� layou� o� � �

"bubble� diagra� tha� show� ho� th� necessar� activitie� an� �

event� for� � sequenc� o� steps� Figur� � i� th� bubbl� diagra� �

o� ou� foundation-buildin� example� Wit� o� withou� PERT� �

specifyin� th� sequenc� o� � project'� step� i� obviousl� a� �

importan� plannin� activity� Mos� contractor� la� ou� th� �

sequenc� o� task� i� � projec� i� som� fashion� bu� PER� make� �

tas� sequencin� � forma� activity� Formalizin� thi� proces� lend� �

valuabl� structur� t� essentia� planning� I� particular� makin� � �

bubbl� diagra� force� th� planne� t� specif� whic� activitie� �

depen� o� th� completio� o� others.

Diagram� lik� tha� show� i� figur� � ar� als� calle� �

networks� � PER� networ� ha� on� initia� event� a� th� extrem� �

left� an� on� termina� event� a� th� extrem� right� th� circle� �

i� figur� � (afte� yo� perfor� � littl� artwork� ar� numbere� an� �

represen� events� Th� line� ar� lettere� an� represen� �

activities� eac� lin� ha� a� arro� indicatin� it� directio� i� �

tim� fro� beginnin� t� completion� Th� networ� a� � whol� show� �

th� serie� o� activitie� tha� mus� b� performe� t� complet� th� �

project� th� arrow� sho� whic� activitie� an� event� logicall� �

preced� others.

A� even� tha� result� fro� completio� o� mor� tha� on� �

activit� i� calle� � merg� event� a� even� tha� represent� th� �

join� beginnin� o� mor� tha� on� activit� i� calle� � burs� �

event� Befor� an� activit� ca� start� al� precedin� activitie� �

mus� b� complete� (bu� no� al� simultaneously)� A� arrow'� lengt� �

an� it� compas� directio� ar� insignificant.

Dashe� line� i� networ� diagram� represen� �

"dummy"activities� � dumm� activit� exist� whe� th� completio� o� �

on� even� depend� o� th� completio� o� anothe� bu� require� n� �

additiona� wor� o� activity� PER� handle� dumm� activitie� lik� �

an� other� bu� assign� th� activit� zer� tim� an� zer� costs.

...T1

#Th� Critica� Path.#

Th� longes� rout� fro� th� beginnin� o� th� networ� o� th� �

lef� t� it� en� o� th� righ� determine� th� tim� require� t� �

complet� th� project� thi� lin� i� th� critica� path� whic� �

determine� th� minimu� tim� require� t� complet� � job� Althoug� ��th� concep� o� � critica� pat� ma� soun� complex� i� i� simpl� �

onc� you'v� lai� � projec� ou� i� � bubbl� diagram.

Critical-pat� analysi� ca� revea� way� t� shorte� th� �

critica� pat� an� t� contro� th� tota� lengt� o� � job� Becaus� �

o� th� siz� o� ou� computer� thi� progra� analyze� th� critica� �

pat� bu� doe� no� attemp� t� shorte� it.

...T1

#Thre� Tim� Estimates.#

Alon� eac� activit� lin� i� figur� 1� yo� se� thre� decima� �

numbers� Thes� number� represen� a� optimistic� likel� an� �

pessimisti� estimat� o� th� tim� require� t� complet� th� �

activity� Eac� tim� th� activit� i� no� o� th� critica� path� � �

manager'� decisio� t� authoriz� expenditure� fo� overtim� woul� �

b� foolis� an� wasteful� Al� activitie� no� o� th� critica� pat� �

hav� "slac� time,� th� differenc� betwee� th� earlies� an� lates� �

expecte� finish� B� definition� onl� th� activitie� o� th� �

critica� pat� hav� zer� slac� time� We'l� elaborat� later.

...T1

#Ou� PER� Program.#

Ou� PER� Progra� i� show� i� listin� 1� � dimensio� (DIM� �

statemen� a� lin� 16� provide� place� t� stor� dat� o� �

activities� Th� sam� DI� statemen� als� provide� storag� fo� � �

dumm� variable,SV� t� b� use� late� durin� sorts.

O� � syste� wit� 32� (remembe� th� articl� wa� writte� fo� � �

TRS-80� byte� o� memor� an� tw� dis� drives� ou� progra� ca� �

handl� mor� tha� 20� activities� W� hav� ye� t� nee� mor� tha� �

10� activities� You� machine'� memor� capacit� an� th� limit� o� �

you� DI� statemen� wil� determin� th� siz� o� th� proble� tha� �

ou� progra� ca� handl� fo� you� Yo� ca� fin� th� limit� b� �

experimentation.

On� wa� t� sav� memor� i� t� carefull� omi� remar� (REM� �

statements(Thes� statement� ar� lef� i� i� fn.f� PERTSAMP.BA� bu� �

hav� bee� remove� fro� PERT80.BA� an� PERT128.BA� i� th� Osborn� �

� version)�

A� note� before� th� critica� pat� consist� o� � serie� o� �

activitie� tha� hav� zer� slac� time� T� fin� th� critica� path� �

yo� mus� identif� activitie� tha� hav� zer� slac� time� Th� �

progra� output� consistin� o� tw� tables� i� designe� t� identif� �

thes� activities.

Th� firs� tabl� (se� listin� 2� show� th� program'� input� �

listin� al� th� activitie� i� th� project� thei� beginnin� an� �

endin� events� an� th� thre� estimate� o� th� tim� eac� activit� �

requires� Yo� shoul� chec� you� inpu� wheneve� yo� us� thi� �

progra� becaus� otherwis� yo� ma� ge� craz� results.

Th� secon� tabl� (se� listin� 3� i� th� program'� output� �

Notic� th� las� column� "Slac� Time.� Zero� i� thi� colum� �

identif� th� critica� path� Yo� can� o� course� trac� th� �

activitie� i� th� critica� pat� b� lookin� i� th� firs� column� �

"Code,� fo� eac� activit� wit� zer� slac� time� Bu� ou� progra� �

als� provide� � men� optio� CRITICA� PAT� AN� TIME� whic� permit� �

bot� th� critica� pat� an� th� tim� require� t� complet� it�

Familiarit� wit� th� projec� an� th� progra� wil� probabl� �

mak� listing� � an� � al� yo� wil� nee� t� full� monito� yo� �

program�  Unfortunately� man� time� ther� wil� b� � nee� t� mak� �

th� schedulin� o� you� projec� understandabl� t� supervisor� o� ��other� withou� detaile� explanation� Thi� i� wher� listin� � �

become� invaluable� Listin� � i� � GANN� char� fo� th� project� �

Thi� char� ca� b� heade� i� eithe� on� o� tw� way� dependin� o� �

th� tim� estimate� i� you� DAT� statements� Thi� wil� b� eithe� �

WEEK� o� MONTHS� Th� GANN� char� heade� i� triggere� b� yo� inpu� �

o� lin� 150� I� yo� ente� WEEK� you� heade� wil� sho� 1� month� �

o� � week� eac� o� PERT8� an� � year�  � week� o� PERT128� I� yo� �

pic� MONTHS� yo� ge� � year� o� month�  � eithe� PERT8� o� �

PERT128� Th� GANN� Char� list� eac� activit� simila� t� listing� �

� an� � an� actuall� merel� provide� � graphi� representatio� o� �

listin� 3�  Th� � represent� th� earl� star� time� Th� � and/o� � �

symbo� represen� th� expecte� tim� fo� th� activit� (C'� i� th� �

activit� i� o� th� Critica� Path)� Th� � i� fo� th� las� finish� �

B�  default� an� spac� betwee� th� las� � fo� a� activit� an� th� �

� represent� slac� tim� i� th� activit� i� starte� a� th� earl� �

star� an� i� finishe� i� th� expecte� time� Ther� wil� b� n� �

spac� betwee� th� las� � an� th� � fo� an� activity� A� stated� �

thes� li� o� th� critica� pat� an� ther� i� n� slac� time�

� wor� o� cautio� abou� usin� th� program� round-of� �

problem� i� calculatio� th� critica� pat� force� u� t� defin� �

zer� slac� tim� a� 0.00� instea� o� tru� zero� Wher� smal� �

difference� ar� important� thi� approximatio� o� zer� ca� caus� �

problems� Th� valu� 0.00� i� entere� i� lin� 1490� perhap� yo� �

ca� chang� th� valu� t� tru� zer� fo� som� o� you� applications� �

Furthermore� sinc� w� use� statistica� method� t� determin� th� �

probabilit� o� � project'� bein� complete� o� time� give� � �

schedule� completio� date� yo� shoul� remembe� tha� dat� �

generate� b� th� progra� i� base� o� estimate� an� i� itsel� a� �

estimate.

...T1

#Runnin� th� Program.#

Th� easies� wa� t� inpu� dat� i� t� us� DAT� statement� a� �

th� en� o� th� progra� startin� alway� a� lin� numbe� 4000� �

Enterin� dat� fro� th� keyboar� take� tim� an� increase� th� �

numbe� o� errors�  Th� bes� wa� d� th� DAT� statement� i� t� boo� �

u� WordSta� i� driv� � an� th� PER� diskett� i� driv� B� Creat� � �

fil� o� driv� � i� th� "N� non-documen� mod� tha� prett� wel� �

discribe� you� project� Lik� "BUILDING.BAS"� Simpl� star� usin� �

lin� 400� wit� th� numbe� o� activitie� an� th� numbe� o� events� �

The� ad� eac� activit� letter� description,startin� an� endin� �

even� an� lastl� th� optimistic� likely� an� pessimesti� times� �

a� below:

400� DAT� 18,9

401� DAT� A,ACCT� PAPERS,1,2,1,2,3

402� DAT� B,SHO� BANKERS,1,3,2,4,6

403� DAT� C,SHO� REA� EST.,1,4,1,13,17

ETC......

Onc� thi� i� done� sav� th� program� No� boo� u� MBASI� an� LOA� �

"x:PERT80� o� "x:PERT128"� MERG� "x:BUILDING� t� appen� you� DAT� �

line� t� th� progra� the� SAV� "x:BUILDING� (x� � th� dis� driv� �

o� choice)� Thi� save� th� entir� progra� unde� th� nam� formerl� �

use� b� you� DAT� line� an� leave� PERT80/12� intac� withou� dat� �

line� an� availabl� fo� futur� projects� Th� followin� ��descriptio� o� � progra� ru� assume� tha� DAT� statement� wer� �

use� fo� input.

Whethe� yo� inpu� dat� fro� DAT� statement� o� th� keyboard� �

th� progra� begin� b� givin� th� identificatio� messag� an� the� �

displays:

**� NOT� BEGINNIN� EVENT�

WIL� B� SORTE� INT�                       �

NUMERICA� ORDE� ***

whe� asking

DIMENSION� FO� ACTIVITIES?_

(NOTE� Thi� wil� onl� appea� i� dat� i� t� b� entere� fro� �

keyboard or disk file.)

TIM� UNIT� WIL� B� MEASURE� IN?_

and

PROJECT START DATE?_

A� yo� se� i� listin� 2� event� ar� arrange� accordin� t� �

th� earlies� startin� even� i� eac� activity� an� tie� ar� broke� �

b� referenc� t� th� earlies� endin� even� fo� eac� activity.

No� th� progra� present� th� inpu� menu:

INPU� MENU

� KEYBOARD

� DIS� FILE

Optio� � cause� th� progra� t� rea� DAT� statement� a� th� �

en� o� th� program� Afte� � brie� delay� th� progra� wil� displa� �

fo� verificatio� th� inpu� o� wha� wa� read.

Th� vide� displa� o� th� inpu� wil� loo� slightl� differen� �

tha� th� tabl� i� listin� � becaus� o� th� difference� i� th� �

scree� an� printe� sizes� I� � singl� scree� won'� accommodat� �

al� th� input� th� progra� wil� as� yo� t� pag� through.

Afte� listin� al� th� input� th� progra� wil� say:

-� ADD� -� T� CONTINU� O� NUMBE� T� CHANGE?_

Th� numbe� referre� t� i� th� numbe� o� an� activit� tha� yo� �

wis� t� change�  Assumin� yo� wan� t� continu� an� ente� -1� th� �

progra� wil� ask:

HAR� COP� O� INPU� DAT� (Y/N)?_

I� yo� reques� har� copy� th� progra� wil� prin� � line� o� EG� �

dat� an� the� asks:

TITLE?_

DATE?_

an� wil� prin� you� responses� a� wel� a� th� measur� o� tim� �

unit� a� th� to� o� th� page� Ou� sampl� se� o� dat� use� th� �

titl� PER� SAMPL� an� th� dat� 11/26/82.�     Afte� th� inpu� i� printed� th� scree� wil� displa� th� �

results� a� show� i� listin� 3� Fo� eac� activity� yo� wil� se� �

computation� o� ho� lon� i� shoul� b� expecte� t� take� th� �

earlies� wee� (yo� ma� us� month� also� i� ca� start� th� �

earlies� i� ca� finish� an� th� slac� tim� (th� differenc� �

betwee� th� earlies� an� lates� possibl� finish)� Yo� ma� hav� t� �

pag� throug� � scree� displa� o� thi� data� Th� progra� wil� �

agai� as� i� yo� wan� har� copy.

Nex� th� GANN� Char� wil� b� displaye� wit� pagin� agai� i� �

necessar� an� � promp� fo� har� copy� Line� 8� an� 9� se� scree� �

an� printe� widt� t� accomodat� al� requirements.

The� yo� wil� see:

OUTPU� MENU

� CRITICA� PAT� AN� TIME

� DISK

� END

� RECYCLE

SELECTION?_

Optio� C� fo� ou� example� result� i� � displa� lik� th� �

following:

CRITICA� PATH

� � � � P

TIM� O� CRITICA� PATH

42.33

SCHEDULE� PROJEC� TIM� (US� SAM� TIM� UNIT� A� DATA)?_

Fo� ou� example� th� critica� pat� consist� o� shoppin� fo� �

� real-estat� agent� obtainin� land� gettin� architectura� plans� �

gettin� � detaile� layou� fo� construction� an� actuall� buildin� �

th� foundation� Th� tim� o� th� critica� pat� i� expecte� t� b� �

42.3� weeks�

Yo� ca� no� inpu� th� schedule� tim� fo� th� project� an� �

th� progra� wil� us� th� � calculation� explaine� i� th� textbo� �

"� Glanc� a� th� Mathematic� o� PERT� t� tel� yo� � probabilit� �

o� meetin� th� schedule� A� show� i� listin� 3� ther� i� � �

0.012385� probabilit� o� finishin� i� 3� week� an� � 0.99053� �

probabilit� o� finishin� i� 5� weeks� A� note� earlier� ther� i� �

als� � .50� probabilit� o� finishin� i� th� expecte� tim� o� th� �

critica� pat� - 42.3� weeks.

...T1

#Conclusion#.

I� yo� nee� hel� plannin� an� schedulin� comple� projects� �

thi� PER� progra� ca� provid� it� Yo� ca� us� i� withou� knowin� �

ho� t� perfor� th� calculation� involved� Althoug� w� repea� ou� �

cautio� abou� relyin� o� estimate-base� estimates� w� stil� �

believ� PER� ha� prove� itsel� � valuabl� manageria� too� an� �

tha� ou� progra� accuratel� represent� PERT.

�           �                                  _

|#2#�                                |#7#|

�

|#8#�

_

�                �                  �                      |#9#|

|#1#�              |#3#�                |#5#|

�                     _

|#4#�                   |#6#�

(NOTE� Sinc� i� i� impossibl� t� dra� � ful� fledge� bubbl� diagra� wit� �

WordStar� perfor� th� followin� upo� printin� thi� documentation� Connec� th� �

bubble� an� labe� th� resultan� line� a� show� below.

1-�  A-1,2,�             4-�  I-8,11,13

1-�  B-2,4,�             5-�  J-2,3,4

1-�  C-2,13,1�           5-�  K-2,5,12

2-�  D-2,4,�             5-�  L-1,2,4

2-�  G-1.4,2.2,6.�       6-�  M-2,3,4

2-�  F-.4,1.3,1.�        6-�  O-1,2,5

2-�  Z-4,5,�             7-�  N-9,11,12

3-�  E-3,4,�             7-�  Q-1,2,3

3-�  H-2,4,�             8-�  P-1,3,6

...T2

#Figur� 1#

Th� PER� networ� diagra� o� th� activitie� require� t� buil� � foundation� �

Eac� circl� represent� a� even� an� eac� lin� betwee� circle� represent� on� o� �

th� activitie� liste� i� tabl� 1� Th� thre� number� give� fo� eac� activit� �

represen� huma� estimate� o� th� optimistic(minimum)� likely� an� �

pessimistic(maximum� tim� i� week� tha� eac� activit� wil� take� Th� networ� ha� �

on� initia� event� even� � a� th� extrem� lef� an� on� termina� event� even� � �

a� th� extrem� right� Th� critica� pat� i� th� on� tha� take� th� mos� tim� t� �

ge� fro� even� � t� even� 9.

�Lette�    Activit�                   Beginnin�     End

Even�      Event

�       assembl� accountin� dat�      �           2

�       loo� fo� ban�                 �           3

�       loo� fo� real-estat� agen�    �           4

�       see� permit�                  �           7

�       mak� marke� stud� o� are�     �           3

�       loo� fo� contracto�           �           5

�       see� insuranc� fo� con-       �           6

struction

�       ge� basi� architectura� plan� �           5

�       mak� cos� stud�               �           4

�       bu� lan�                      �           5

�       lis� material�                �           6

�       ge� mor� detaile� architec-   �           7

tura� plans

�       hav� surve� mad�              �           8

�       bu� firs� batc� o� material�  �           8

�       bu� secon� batc� o�           �           9

materials

�       complet� detaile� interna�    �           8

layou� o� foundation

�       hir� cre�                     �           9

�       buil� foundatio�              �           9

...T2

#Tabl� 1#

Th� activitie� require� t� buil� � foundation� th� progra� i� listin� � use� th� �

letter� a� lef� t� identif� th� activities� Th� tw� column� a� righ� lis� th� �

firs� an� las� even� durin� eac� activity� A� even� i� th� completio� o� on� o� �

mor� activities.

�...T2

#� Glanc� a� th� Mathematic� o� PERT#

Th� mathematic� o� PER� involve� som� interestin� �

statistica� concepts� Yo� don'� hav� t� understan� th� �

mathematic� t� us� PERT� bu� i� help� yo� t� understan� ho� ou� �

progra� works.

First� w� mus� refres� you� recollectio� o� som� basi� �

statistica� terms� th� mea� o� � se� o� occurence� o� som� �

variabl� i� th� arithmeti� averag� o� th� value� o� th� �

occurences� th� standar� deviatio� i� th� squar� roo� o� th� mea� �

o� th� square� o� th� deviation� o� individua� occurence� fro� �

th� mean)� th� varianc� i� th� squar� o� th� standar� deviation.

Fo� example� i� w� hav� thre� value� 9.1� an� 15� thei� mea� �

i� 36/3=12� thei� varianc� is

(9-12)� � (12-12)� � (15-12)� � 18

an� th� standar� deviatio� i� th� squar� roo� o� 18� whic� i� �

approximatel� 4.24.

I� i� � commo� statistica� assumptio� tha� th� standar� �

deviatio� i� unimoda� distribution� (distribution� tha� hav� onl� �

� singl� most-likel� occurrin� value� i� roughl� � sixt� o� th� �

rang� o� distributio� lie� wit� thre� standar� deviation� o� th� �

mean� an� fo� th� norma� distribution� 99.� percen� o� th� �

distributio� lie� withi� thre� standar� deviation� o� th� mean.

Sinc� w� hav� estimate� o� th� minimu� tim�  �  an� th� �

maximu� tim�  �  require� t� complet� a� activity� w� hav� �

establishe� a� estimate� rang� o� actua� times� W� ca� estimat� �

th� standar� deviatio� o� th� actua� tim� as

#(b-a)#

6

Sinc� PER� assume� tha� chance� o� rando� factor� wil� �

influenc� th� actua� tim� neede� t� complet� a� activity� w� ca� �

expec� th� actua� time� t� b� distribute� alon� som� curve� PER� �

assume� tha� th� mea� actua� tim� wil� follo� th� distributio� �

know� a� th� bet� distribution� whic� i� containe� i� � finit� �

interva� an� ma� b� eithe� symmetri� o� skewed� Ou� mos� likel� �

tim� o� completio�  �  i� th� mod� o� th� curv� fo� eac� �

activity� th� followin� equation� base� o� th� assumptio� tha� �

ou� formul� fo� th� standar� deviatio� i� correct� i� linea� �

approximatio� o� th� valu� o� th� expecte� value� EV� o� th� mea� �

time:

(a+4xm+b)

E� � ----------

6

A� yo� ca� see� thi� i� jus� � weighte� average� countin� th� �

minimu� an� maximu� eac� onc� an� th� mod� fou� times� the� �

dividin� th� tota� b� 6� O� lin� 99� o� listin� 1� sam� equatio� �

i� expresse� as:

A(I,6)=(A(I,3)+4*A(I,4)+A(I,5)/6�

Th� followin� equatio� give� th� varianc� o� th� bet� �

distributio� fo� eac� activity:

VA� =((b-a)/6)2

Fo� eac� activity� th� progra� applie� th� statistica� �

principle� describe� abov� an� calculate� th� tim� th� activit� �

shoul� last� th� earlies� tim� a� whic� i� ca� start� th� �

earlies� finish� th� lates� start� an� th� lates� finish� �

Calculatio� o� th� earlies� star� an� finis� time� i� calle� th� �

"forwar� pass� an� take� plac� i� ou� progra� a� line� 97� t� �

1080� Calculatio� o� th� lates� star� an� finis� i� calle� th� �

"backwar� pass� an� take� plac� a� line� 109� t� 1230.

Th� differenc� betwee� th� earlies� an� lates� projecte� �

finis� fo� eac� activit� i� calle� "slac� time"� A� line� 124� t� �

1290� th� progra� calculate� slac� tim� fo� eac� activity� Th� �

even� tha� hav� zer� slac� tim� for� th� critica� path.

T� obtai� th� approximat� varianc� fo� th� critica� path� �

ad� th� variance� o� th� activitie� o� th� path:

VAR(Path)=VAR(1)+VAR(2� ....+VAR(n)

I� happen� tha� th� Centra� Limi� theore� enable� us� base� o� �

th� foregoing� t� assum� tha� th� distributio� o� th� tim� �

require� t� complet� th� critica� pat� i� normal� Base� o� thi� �

assumption� w� ca� calculat� th� probabilit� o� th� project'� �

bein� o� time� give� som� specifie� targe� completio� time� Th� �

calculation'� basi� i� th� deviatio� o� th� schedule� completio� �

tim� fro� th� estimate� mea� completio� wit� th� deviatio� �

measure� i� unit� o� standar� deviations� Thi� deviatio� i� �

calle� Z� Th� � calculatio� fo� th� standar� norma� tabl� is:

(schedule�             tim� o�  )

�   tim�           critica� path)

� � ----------------------------------

VAR(Path)

Rathe� tha� requir� yo� t� us� norma� table� wit� ou� �

program� w� hav� buil� i� � Taylo� serie� t� approximat� th� �

tables� (� Taylo� serie� i� � powe� serie� tha� give� th� �

expansio� o� � functio�  f(x�  i� th� neighborhoo� o� � poin� a� �

provide� al� derivative� exis� an� � serie� converges.� Th� �

Taylo� serie� i� locate� a� lin� 244� an� followin� i� ou� �

program.

Th� expecte� tim� o� th� critica� pat� i� th� su� o� th� �

expecte� time� o� al� th� activitie� o� th� path� I� th� �

schedule� tim� o� th� projec� equal� th� expecte� tim� o� th� �

critica� path� yo� hav� � 5� percen� chanc� o� completin� th� �

projec� o� time.

##########################################################################################################################